## WBS
WBS Code | Task | Optimistic Cost | Cost | Pessimistic cost | Risk - Impact | Risk - Likelihood | Risk - Score | Risk % multiplier | Duration (days) | Optimistic Duration | Pessimistic Duration | Predecessors | Time-dependent %
1 | Milestone 01 - Discovery and Design | - | 21700 | -
1.1 | Stakeholder workshops | - | 3500 | - | 2 | 2 | 4 | 0.2 | 10 | - | - | - | 80%
1.2 | Requirements and process mapping | - | 5600 | - | 2 | 3 | 6 | 0.4 | 15 | - | - | 1.1 | 80%
1.2.1 | Data audit of legacy systems | - | 4200 | - | 3 | 4 | 12 | 0.6 | 12 | - | - | 1.1 | 70%
1.3 | Solution architecture | - | 7000 | - | 3 | 2 | 6 | 0.4 | 15 | - | - | 1.2 | 70%
1.4 | Design sign-off and governance | - | 1400 | - | 1 | 2 | 2 | 0.2 | 5 | - | - | 1.3, 1.2.1 | 50%
2 | Milestone 02 - Build and Integration | - | 46900 | -
2.1 | Core platform configuration | - | 16800 | - | 3 | 3 | 9 | 0.4 | 30 | - | - | 1.4 | 50%
2.2 | Data migration scripts | - | 11200 | - | 4 | 4 | 16 | 0.6 | 25 | - | 40 | 1.4 | 60%
2.3 | Third-party integrations | 9000 | 12600 | 18000 | 5 | 5 | 25 | 0.8 | 30 | 20 | 55 | 2.1 | 40%
2.4 | Reporting dashboards | - | 6300 | - | 2 | 2 | 4 | 0.2 | 15 | - | - | 2.1 | 60%
3 | Milestone 03 - Testing | - | 22400 | -
3.1 | System testing | - | 8400 | - | 2 | 3 | 6 | 0.4 | 15 | - | - | 2.2, 2.3, 2.4 | 80%
3.2 | User acceptance testing | - | 5600 | - | 2 | 4 | 8 | 0.4 | 10 | - | - | 3.1 | 80%
3.3 | Performance and security testing | - | 4900 | - | 3 | 3 | 9 | 0.4 | 10 | - | - | 3.1 | 60%
3.3.1 | Remediation of test defects | - | 3500 | - | 4 | 3 | 12 | 0.6 | 8 | - | 15 | 3.3 | 70%
4 | Milestone 04 - Deployment and Handover | - | 15400 | -
4.1 | Cut-over planning | - | 2800 | - | 1 | 2 | 2 | 0.2 | 5 | - | - | 3.2 | 80%
4.2 | Go-live and hypercare | - | 7000 | - | 3 | 4 | 12 | 0.6 | 15 | - | - | 4.1, 3.3.1 | 70%
4.3 | Training and user guides | - | 4200 | - | 1 | 3 | 3 | 0.2 | 10 | - | - | 3.2 | 60%
4.4 | Project closure and lessons learned | 1200 | 1400 | 2100 | 1 | 1 | 1 | 0.2 | 5 | 4 | 8 | 4.2, 4.3 | 80%
Fictional sample project for demonstration. Replace with your own WBS; keep the column headings.

## Risk Register
Risk register: each risk either happens (by its probability) or not. Cost impacts are added to the total; schedule impacts extend the affected task.
Risk ID | Risk | Owner | Probability (%) | Cost impact min | Cost impact most likely | Cost impact max | Schedule impact min (days) | Schedule impact most likely (days) | Schedule impact max (days) | Affected task
R1 | Integration vendor delivers its API late | Technical lead | 40 | 3000 | 6000 | 12000 | 5 | 10 | 20 | 2.3
R2 | Legacy data quality worse than the audit suggested | Data lead | 50 | 2000 | 4000 | 8000 | 3 | 8 | 15 | 2.2
R3 | Key business experts unavailable during UAT | Business sponsor | 30 | 1000 | 2000 | 4000 | 3 | 5 | 10 | 3.2
R4 | Security testing finds a critical vulnerability | Security lead | 25 | 3000 | 5000 | 10000 | 5 | 10 | 20 | 3.3.1
R5 | Regulator requests a scope change mid-build | Project manager | 15 | 5000 | 10000 | 20000 | 10 | 15 | 30 | 2.1
R6 | Software licence price rises at renewal | Commercial lead | 35 | 1500 | 2500 | 4000 | 0 | 0 | 0

## Risk Matrix
Risk score = Impact (1-6) x Likelihood (1-6)
Score | Band | Risk % multiplier
25 to 36 | Red | 0.8
12 to 24 | Orange | 0.6
6 to 11 | Yellow | 0.4
1 to 5 | Green | 0.2
Each task's cost is loaded by (1 + multiplier) before simulation. Set multipliers to 0 to model estimate uncertainty only.